## Notes
The following shows the cost analysis of data for a potential project and its associated costs and benefits
Project A
| Upfront Cost | 50000
| Recurring Cost | 20000
| Revenue after Year 0 | 38000
| Discount Rate | 12%
Project B
| Upfront Cost | 25000
| Recurring Cost | 10000
| Revenue after Year 0 | 15000
| Discount Rate | 7%
Project C
| Upfront Cost | 100000
| Recurring Cost | 70000
| Revenue after Year 0 | 85000
| Discount Rate | 5%
Recommendation
The recommendation for the best project is Project A and Project C.
Project A having the nearest break even point of the three options. It also carries the highest risk, suggested by the highest interest rate and most variation in the present value.
Project C seems like the best option as it produces the most revenue by year 10, has acceptable risk, but the break even point being the longest

## Cost Analysis and Break Even
Project A
| Year | IR | PV Factor | Benefit | PV of Benefit | Cumulative Benefit | Cost | PV of Cost | Cumulative Cost | Difference of Cumulative Totals
| 0 | 0.12 | 1 | 0 | 0 | 0 | 50000 | 50000 | 50000 | -50000
| 1 | 0.12 | 0.89286 | 38000 | 33928.5714 | 33928.5714 | 20000 | 17857.1429 | 67857.1429 | -33928.5714
| 2 | 0.12 | 0.79719 | 38000 | 30293.3673 | 64221.9388 | 20000 | 15943.8776 | 83801.0204 | -19579.0816
| 3 | 0.12 | 0.71178 | 38000 | 27047.6494 | 91269.5882 | 20000 | 14235.605 | 98036.6254 | -6767.0372
| 4 | 0.12 | 0.63552 | 38000 | 24149.687 | 115419.2752 | 20000 | 12710.3616 | 110746.9869 | 4672.2882
| 5 | 0.12 | 0.56743 | 38000 | 21562.2205 | 136981.4957 | 20000 | 11348.5371 | 122095.524 | 14885.9716
| 6 | 0.12 | 0.50663 | 38000 | 19251.9826 | 156233.4783 | 20000 | 10132.6224 | 132228.1465 | 24005.3318
| 7 | 0.12 | 0.45235 | 38000 | 17189.2702 | 173422.7485 | 20000 | 9046.9843 | 141275.1308 | 32147.6177
| 8 | 0.12 | 0.40388 | 38000 | 15347.5627 | 188770.3111 | 20000 | 8077.6646 | 149352.7953 | 39417.5158
| 9 | 0.12 | 0.36061 | 38000 | 13703.1809 | 202473.4921 | 20000 | 7212.2005 | 156564.9958 | 45908.4963
| 10 | 0.12 | 0.32197 | 38000 | 12234.983 | 214708.4751 | 20000 | 6439.4647 | 163004.4606 | 51704.0145
Project B
| Year | IR | PV Factor | Benefit | PV of Benefit | Cumulative Benefit | Cost | PV of Cost | Cumulative Cost | Difference of Cumulative Totals
| 0 | 0.07 | 1 | 0 | 0 | 0 | 25000 | 25000 | 25000 | -25000
| 1 | 0.07 | 0.95264 | 15000 | 14289.57 | 14289.57 | 10000 | 9526.38 | 34526.38 | -20236.81
| 2 | 0.07 | 0.92598 | 15000 | 13889.697 | 28179.267 | 10000 | 9259.798 | 43786.178 | -15606.911
| 3 | 0.07 | 0.90752 | 15000 | 13612.7873 | 41792.0543 | 10000 | 9075.1916 | 52861.3695 | -11069.3152
| 4 | 0.07 | 0.89345 | 15000 | 13401.807 | 55193.8613 | 10000 | 8934.538 | 61795.9075 | -6602.0462
| 5 | 0.07 | 0.88212 | 15000 | 13231.8531 | 68425.7144 | 10000 | 8821.2354 | 70617.1429 | -2191.4285
| 6 | 0.07 | 0.87266 | 15000 | 13089.8418 | 81515.5561 | 10000 | 8726.5612 | 79343.7041 | 2171.852
| 7 | 0.07 | 0.86454 | 15000 | 12968.0585 | 94483.6146 | 10000 | 8645.3723 | 87989.0764 | 6494.5382
| 8 | 0.07 | 0.85744 | 15000 | 12861.5788 | 107345.1934 | 10000 | 8574.3859 | 96563.4623 | 10781.7311
| 9 | 0.07 | 0.85114 | 15000 | 12767.0706 | 120112.264 | 10000 | 8511.3804 | 105074.8427 | 15037.4213
| 10 | 0.07 | 0.84548 | 15000 | 12682.1759 | 132794.4399 | 10000 | 8454.7839 | 113529.6266 | 19264.8133
Project 3
| Year | IR | PV Factor | Benefit | PV of Benefit | Cumulative Benefit | Cost | PV of Cost | Cumulative Cost | Difference of Cumulative Totals
| 0 | 0.05 | 1 | 0 | 0 | 0 | 100000 | 100000 | 100000 | -100000
| 1 | 0.05 | 0.96594 | 85000 | 82104.588 | 82104.588 | 70000 | 67615.543 | 167615.543 | -85510.9551
| 2 | 0.05 | 0.94655 | 85000 | 80456.8199 | 162561.4079 | 70000 | 66258.5576 | 233874.1006 | -71312.6927
| 3 | 0.05 | 0.93303 | 85000 | 79307.8043 | 241869.2122 | 70000 | 65312.3094 | 299186.41 | -57317.1979
| 4 | 0.05 | 0.92268 | 85000 | 78427.8709 | 320297.0831 | 70000 | 64587.6584 | 363774.0684 | -43476.9853
| 5 | 0.05 | 0.91431 | 85000 | 77716.1653 | 398013.2484 | 70000 | 64001.5479 | 427775.6163 | -29762.3679
| 6 | 0.05 | 0.90729 | 85000 | 77119.4678 | 475132.7162 | 70000 | 63510.1499 | 491285.7662 | -16153.0501
| 7 | 0.05 | 0.90125 | 85000 | 76606.2893 | 551739.0055 | 70000 | 63087.5324 | 554373.2986 | -2634.2932
| 8 | 0.05 | 0.89596 | 85000 | 76156.4691 | 627895.4746 | 70000 | 62717.0922 | 617090.3908 | 10805.0837
| 9 | 0.05 | 0.89125 | 85000 | 75756.3297 | 703651.8043 | 70000 | 62387.5657 | 679477.9565 | 24173.8478
| 10 | 0.05 | 0.88701 | 85000 | 75396.1711 | 779047.9754 | 70000 | 62090.9645 | 741568.9209 | 37479.0545